## How To Use
KSA Implementation Backlog
This backlog sequences the work to address NCA (ECC + CCC) and PDPL controls using the LZA Universal Configuration (UC) plus the KSA supplement.
Phases:
Phase 1 — Deploy UC baseline: gives you the 57-control infrastructure baseline. Do this first.
Phase 2 — Apply KSA enhancements: the SCPs, tag policy, and backup policy in this supplement.
Phase 3 — Additional AWS services: addressable controls needing config beyond LZA defaults.
Phase 4 — Your organizational responsibility: non-technical controls (governance, HR, training, email, MDM, pen testing, audit).
PDPL Tasks sheet: data protection tasks mapped to PDPL articles.
Note: This backlog is implementation guidance, not a compliance attestation. Compliance is a shared outcome between these technical controls and your organizational policies and processes. Framework versions: ECC-2:2024, CCC-2:2024, PDPL (2023, enforced Sep 2024).
Use the Status column to track progress. Adjust priorities to your regulatory scope.

## Implementation Backlog
Task ID | Phase | Task | What it does | NCA / PDPL controls | Priority | Status
| PHASE 1 — DEPLOY UC BASELINE | Deploying the LZA Universal Configuration delivers the 57-control infrastructure baseline (security services, logging, guardrails). Do this first.
UC-1 | Phase 1 | Deploy the LZA Universal Configuration | Deploy UC as documented. This provisions multi-account OUs, centralized logging, GuardDuty, Security Hub, Inspector, Macie, Config, CloudTrail, IAM Access Analyzer, IAM password policy, EBS/S3 encryption defaults, and LZA self-protection guardrails. | 31 ECC + 26 CCC (per Workbook) | High
UC-2 | Phase 1 | Confirm UC RCPs and data-perimeter policies are enabled | Verify UC v1.3.0+ data-perimeter RCPs (aws:PrincipalOrgID on STS, SQS, Secrets Manager, S3) are active. If on an earlier version, add data-perimeter RCPs. | ECC 2-7, CCC 2-6-T, PDPL Art. 29 | High
| PHASE 2 — APPLY KSA ENHANCEMENTS | Layer the KSA-specific configuration files on top of the UC baseline. These address NCA requirements UC does not cover out of the box.
KSA-1 | Phase 2 | Apply region restriction SCP | Deploy scp-region-restriction.json at the root OU. Replace region placeholders with your approved AWS Region(s). | ECC 2-5, ECC 2-7, CCC 2-6-T, PDPL Art. 29 | High
KSA-2 | Phase 2 | Apply data residency SCP | Deploy scp-data-residency.json to workload OUs. Denies cross-region replication, VPN/Global Accelerator egress, and public RDS. | ECC 2-7, PDPL Art. 29 | High
KSA-3 | Phase 2 | Apply identity governance SCP | Deploy scp-identity-governance.json. Blocks IAM user creation and forces federated access via IAM Identity Center. | ECC 2-2 | High
KSA-4 | Phase 2 | Apply DataClassification tag policy | Deploy ksa-tag-policy.json. Enforces valid DataClassification tag values on S3, RDS, EC2, DynamoDB, EFS, Lambda. Start in report mode, then enforce. | ECC 2-1-5, ECC 2-7, PDPL Art. 6 | High
KSA-5 | Phase 2 | Apply tag-presence SCP (optional) | Deploy scp-require-data-classification-tag.json to a test OU first. Denies resource creation without the DataClassification tag. Expand after teams adopt tagging. | ECC 2-1-5, PDPL Art. 6 | Medium
KSA-6 | Phase 2 | Apply extended backup schedules | Deploy ksa-backup-policies.json. Adds NinetyDay/Yearly schedules. Set retention days to your documented requirements; provision the vault and role first. | ECC 2-9 | Medium
KSA-7 | Phase 2 | Configure IAM Identity Center with your IdP | Federate to your identity provider, enforce MFA, define scoped permission sets with session limits. | ECC 2-2 | High
KSA-8 | Phase 2 | Configure security alerting (EventBridge + SNS) | Route Security Hub / GuardDuty findings to SNS topics by severity for real-time notification. | ECC 2-13 | Medium
| PHASE 3 — ADDITIONAL AWS SERVICES (beyond LZA defaults) | Addressable NCA controls that need AWS services configured beyond the UC baseline and KSA SCPs.
ADD-1 | Phase 3 | Deploy AWS WAF with managed rule groups | Protect public web applications. Addresses web application security. | ECC 2-15, CCC web app controls | Medium
ADD-2 | Phase 3 | Configure SSM Patch Manager baselines | Automate OS patching on a defined cadence. Addresses vulnerability remediation. | ECC 2-10 | Medium
ADD-3 | Phase 3 | Run Macie classification jobs on data stores | Scan S3 for personal data, feed classification into tagging and access decisions. | ECC 2-7, PDPL Art. 19 | Medium
ADD-4 | Phase 3 | Enforce TLS on data services (S3, ALB, CloudFront) | Require aws:SecureTransport; deploy ALB/CloudFront with TLS termination. | ECC 2-8 | Medium
ADD-5 | Phase 3 | Integrate with your SIEM | Forward Security Hub / CloudTrail to your SIEM for correlation and retention. | ECC 2-12 | Medium
| PHASE 4 — YOUR ORGANIZATIONAL RESPONSIBILITY | Non-technical controls no cloud platform addresses. Plan these in your broader program. See the Org Responsibility Controls sheet in the mapping.
ORG-1 | Phase 4 | Document and approve cybersecurity strategy | Board-approved strategy aligned to NCA. | ECC 1-1 | High
ORG-2 | Phase 4 | Establish cybersecurity function and committee | Stand up the department and supervisory committee. | ECC 1-2 | High
ORG-3 | Phase 4 | Document cybersecurity policies and procedures | Write, approve, and maintain policy documents. | ECC 1-3 | High
ORG-4 | Phase 4 | Define risk management methodology | Establish risk assessment and treatment process; maintain a risk register. | ECC 1-5 | High
ORG-5 | Phase 4 | Define HR cybersecurity requirements | Background checks, employment clauses, joiner/mover/leaver. | ECC 1-9 | Medium
ORG-6 | Phase 4 | Implement awareness and training program | Deliver periodic security training and phishing awareness. | ECC 1-10 | Medium
ORG-7 | Phase 4 | Implement email security controls | Configure SPF/DKIM/DMARC and filtering on your email platform. | ECC 2-4 | Medium
ORG-8 | Phase 4 | Deploy and configure MDM | Manage and secure endpoints; enable secure disposal. | ECC 2-6, CCC 2-5-T | Medium
ORG-9 | Phase 4 | Conduct penetration testing | Engage qualified providers for periodic testing. | ECC 2-11-4 | Medium
ORG-10 | Phase 4 | Define third-party cybersecurity requirements | Vendor security clauses and reviews. | ECC 4-1 | Medium
ORG-11 | Phase 4 | Schedule periodic reviews and NCA audit | Quarterly access reviews, monthly Security Hub review, annual NCA compliance audit with independent auditors. | ECC 1-8 | Medium

## PDPL Tasks
Task ID | Task | What it does | PDPL articles | Priority | Status
PDPL-1 | Configure data retention lifecycle policies | S3 Lifecycle rules to delete personal data after its retention period; do not keep longer than needed. | Art. 18 (retention/minimization) | High
PDPL-2 | Implement encryption for personal data | KMS encryption at rest, TLS in transit for personal data stores. | Art. 19 (security measures) | High
PDPL-3 | Enforce cross-border transfer restriction | Region restriction SCP prevents personal data leaving approved regions. | Art. 29 (cross-border transfer) | High
PDPL-4 | Build breach detection and notification process | Detect incidents (GuardDuty/Security Hub) and notify SDAIA within 72 hours. | Art. 20 (breach notification) | High
PDPL-5 | Configure audit logging for personal data processing | CloudTrail data events on personal-data buckets; retain for audit. | Art. 30-31 (records of processing) | Medium
PDPL-6 | Run Macie for personal data discovery | Discover and classify PII in S3; drive DataClassification tagging. | Art. 6 (classification) | Medium
PDPL-7 | Implement data minimization controls | Limit collection and access to what is necessary for the stated purpose. | Art. 10-11 (minimization/purpose) | Medium
PDPL-8 | Build data subject access request (DSAR) workflow | Process to fulfil access, correction, and deletion requests. | Art. 4 (data subject rights) | Medium
PDPL-9 | Implement consent management | Capture, store, and honor consent for personal data processing. | Art. 5-7 (consent/legal basis) | Medium
PDPL-10 | Conduct privacy impact assessment | Assess processing activities that pose higher risk to data subjects. | Art. 25 (impact assessment) | Medium
PDPL-11 | Configure IAM least privilege for personal data | Scope access to personal-data stores to authorized roles only. | Art. 19 (access control) | Medium
PDPL-12 | Configure deprovisioning (SCIM) | Automatic access removal on leaver events via Identity Center SCIM. | Art. 19 (access control) | Medium